## Cover Page
Bill Payment System
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Bobburi Sri Harsha
Role
Signature
| Date | 2019-12-02
Project ID: Car Servicing | 144 |  |  | <SCI.ID> / Ver: <No.>
C3: Protected
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog <Instructions> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Sprint 1/2
The Sprint sheets has to be filled for each sprint
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
| Feature Id | List the feature id taken from product backlog that are selected to be completed in the particular sprint.
| Task No | List the number tasks the feature is split into.
| Task | Name the tasks the feature is split into.
| Owner | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5/6 | Task done in Day1/2/3/4/5/6 - Sprint review and retrospective to be held on Day 6
| Total | Summation of the estimation of the per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint 1
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
Req_1 | Task_1 | When the user clicks on the registration link, system should re-direct to registration form and provide two options: Register as Customer Register as Admin | harshabobburi | 0.5 | 0.25 | [5 empty] | Completed
Req_1 | Task_2 | User to fill the basic attributes.User failing to provide information for the mandatory fields be presented with an alert message. Post-successful field validation, save the information in the database | harshabobburi | 0.5 | 0.25 | [5 empty] | Completed
Req_2 | Task_1 | A registered user is able click ‘Login’ link, after keying in ‘UserID’ & ‘Password’ field and get his credentials authenticated with the existing database entry.If a registered user is unable to login and get his credentials authenticated, The user is presented with relevant error messages. | harshabobburi | 0.5 | 0.25 | [5 empty] | Completed
Req_3 | Task_1 | Vendor clicks on the “Register Vendor” button and display a portal to display a form to enter the required details. | harshabobburi | 0.5 |  | 0,25 |  |  |  |  | Completed
Req_3 | Task_2 | The display form should have buttons to “Register” or “Reset” the fields.Clicking on Register button should save the details to the database.Clicking “Reset” button should clear all the fields | harshabobburi | 0.5 |  | 1 |  |  |  |  | Completed
Req_4 | Task_1 | Admin On login should be able to view the list of newly registered vendors and also able to view the details of the vendors. | harshabobburi | 0.5 |  |  | 0.75 |  |  |  | Completed
Req_4 | Task_2 | Admin should be have rights to accept/send for correction/reject any vendor.Only on accepting, a vendor gets activated and will be available for user and on rejection will not be available for users. | harshabobburi | 1 |  |  | 0.25 |  |  |  | Completed
Req_5 | Task_1 | Vendor should be allowed to update the registered vendor details as and when required | harshabobburi | 0.5 |  |  |  | 0.25 |  |  | Completed
Req_6 | Task_1 | User on login should be able to see the available services and search option based on category-bill type/vendor and should be able see the bill details. | harshabobburi | 0.5 |  |  |  | 0.5
Req_6 | Task_2 | Customer to be provided with option to record the type of bills payed regularly.Based on the type of bill selected, procure the required details and store in the Database. | harshabobburi | 0.5 |  |  |  | 0.5
Req_6 | Task_3 | rovide an option if the user wants to set reminders to pay the bills and choose the frequency of reminder and verify user contact information is updated | harshabobburi | 0.5 |  |  |  |  | 1
Req_7 | Task_1 | Portal to select the type of bill to be payed. Post the bill type is selected, Portal to verify the registered/updated information in the Database and the pending amount to be payed. | harshabobburi | 0.5 | [5 empty] | 0.75
Req_7 | Task_2 | User to select the payment method.Based on the selected payment type, portal to display the form to enter the required details. Validate the provided details against the banks and display a message. | harshabobburi | 0.5 | [5 empty] | 0.25
|  | Total |  | 7 | 0.75 | 1 | 1 | 1.25 | 1 | 1
Sprint Goal
Some sprint goal

## Sprint 2
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
Req_6 | Task_1 | User on login should be able to see the available services and search option based on category-bill type/vendor and should be able see the bill details. | Bobburi Sri Harsha | 1 |  |  |  | 1 |  |  | Completed
Req_6 | Task_2 | Customer to be provided with option to record the type of bills payed regularly.Based on the type of bill selected, procure the required details and store in the Database. | Bobburi Sri Harsha | 2 |  |  |  | 1 | 1 |  | Completed
Req_6 | Task_3 | Provide an option if the user wants to set reminders to pay the bills and choose the frequency of reminder and verify user contact information is updated. | Bobburi Sri Harsha | 1 |  |  |  |  | 1 |  | N/A
Req_7 | Task_1 | Portal to select the type of bill to be payed. Post the bill type is selected, Portal to verify the registered/updated information in the Database and the pending amount to be payed. | Bobburi Sri Harsha | 2 |  |  |  |  | 1 |  | Completed
Req_7 | Task_2 | User to select the payment method.Based on the selected payment type, portal to display the form to enter the required details. Validate the provided details against the banks and display a message. | Bobburi Sri Harsha | 1 |  |  |  |  | 1 | 1 | N/A
|  | Total |  | 7 | 0 | 0 | 0 | 2 | 4 | 1
Sprint Goal
Some sprint goal

## Data (hidden)
In-Progress
Completed
N/A